Summary of Recommended Tasks
# Planning Phase
- Define Budget for: Purchase, Infrastructure and Connectivity, Staff.
- Hire project manager and Core Team managers.
- Select Target community (schools, centers).
- Define XO specs.
# Deployment Phase
- Hire staff for Core Team.
- Arrange training for Core Team with OLPC.
- Develop Laptop Distribution Plan.
- Design and collect data for Baseline Study.
- Prepare Infrastructure and Connectivity (at schools and community level).
- Organize and Perform Teacher Training.
- Laptop Distribution.
# Post-Deployment Phase
- Design and perform Tech support strategy for Laptop Maintenance and Repairs.
- Design and supervise Learning Environments with the XO: Formal (in school, classroom),
- Non-Formal (extracurricular activities), Informal (home, family).
- Perform follow up teacher trainings.
- Design and apply Evaluation studies (for students learning and project implementation).